## Sheet1
Sample MSA Process, Timing and LOE Outline: This tool, downloaded from the BEAM Exchange, is part of the MSA Toolkit. It is an Excel document listing the key MSA process steps with LOE and timing estimates, including a GAANT. It is a very useful tool to consider in as early as the proposal stage to inform budgeting, or in anticipation of an actual MSA in the start-up phase of a new activity. The information can also feed into a ToR for a consultant/firm leading the MSA.
Operational planning of the MSA | Purpose/activities | Sub-activities | LOE estimates (# days for one person) | Notes | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
Proposal stage | Understand the key challenges and potential solutions of the development challenge presented in the solicitation document | Conduct secondary research, inputs from team members and potentially some primary research | 2024-02-10 | This is very context-dependent (size of opportunity, scope, previous organizational experience, etc.) | Proposal stage (blue)
| Consider: timing, scope (how many market systems), context, led in-house or via consultant, research team staffing, and budget | Narrative | 0.25 | Led by MSA focal point
|  | Budget | 0.5
Start-up/inception phase stage | Identify MSA focal point and MSA lead, revisit MSA research team staffing, timing, context, physical space, budget | Draft ToR for MSA lead (if external) | 0.5 | Led by MSA focal point | Start-up stage (yellow)
|  | Recruit MSA lead (if external) | 2 | Led by MSA focal point and recruiter(s)
|  | Revisit MSA research aspects | 1 | Led by MSA focal point in collaboration with project leadership
LOE and Gantt chart based on rough estimates for a full MSA effort for a new activity deep diving into 3 market systems
The market systems analysis process | Critical information needs (i.e. questions) | Sub-activities | LOE estimates (# days for one person) | Notes | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21
Set-up | What are our impact objectives? What are we trying to achieve and for whom? | Develop draft MSA report outline | 0.25 | This should have been started by the MSA focal point and perhaps included in the ToR if hiring a consultant. The outline will likely continue to evolve throughout the MSA effort until the end. | MSA process stage (green)
|  | Develop draft research plan outline and initial rough description | 1 | It would be helpful if the MSA focal point already has an idea of what they want the research plan to include.
|  | Advanced draft of research plan | 1.5
|  | Organize and train research team | 1 | The MSA focal point must be involved in this step, especially when hiring an outside consultant.
|  | Conduct kick-off meeting | 2024-01-03 | The activity leadership, MSA focal point and research team members should participate.
System selection & prioritization of research areas | Which market systems are best suited to achieve our objectives? | Defining selection criteria | 0.5 | This is a critical step and must be approved by the MSA focal point
Gathering, analyzing, & summarizing information
|  | Secondary | 5 | Assuming around 5 potential market systems are considered
|  | Primary | 2024-03-09
|  | Scoring and selection | 1 | Ideally done with MSA focal point and other activity leaders, potentially including MSA research team
|  | Validation | 0.5 | Validation via market actors
|  | Prioritization and revision of research areas | 0.5 | This step is about revising the research plan
System Analysis
System overview/mapping | How do these systems need to shift/change in order to better address the needs of our target group(s)? What factors are preventing the system from changing, or “getting there”? What factors have initiated/supported change in the past? Which system actors initiate/support change (e.g. leverage points, influencers)? What are these actors’ interests, incentives and capacities? | Revising and deepening understanding of the market systems overview | 3 | Only counting secondary literature review throughout the remaining MSA process as primary data gathering is listed as a sub-activity below.
|  | Initial systems mapping | 3 | This initial mapping is updated as part of the primary data gathering sub-activity
Identifying “underlying dynamics” preventing or propelling the system to shift to a more desirable state |  | Primary data gathering, analyzing, sense-making, summarizing | 15-45 | NOTE - LOE for one person only (e.g. MSA lead). If more individuals are hired, this needs to be updated, as well as the timing aspects. | [10 empty] | MSA process for smaller teams would take longer, especially for primary data gathering (purple)
Validation |  | Validation via market actors | 0.5-1 | Via a workshop or individual meetings
The market system strategy and intervention design process
System visioning | What is the “adjacent possible” in terms of systems change? Which direction of system transformation can realistically be envisioned? |  | 3 | Ideally MSA focal point and activity leadership participate
Intervention design process | Which interventions and partnerships are most likely to trigger the envisioned system changes? | Development and prioritization of intervention areas | 1 | Ideally MSA focal point and activity leadership participate
|  | Drafting potential probe interventions and partnerships | 6 | Ideally MSA focal point and activity leadership participate
Feasibility checks | Are the proposed interventions and partnership approaches feasible based on what we know (e.g. incentives, system dynamics, power/influence, history and the system’s trajectory)? |  | 2024-03-06 | Feasibility of opportunity, solution, partner and measurement
MSA report development
Drafting of internal MSA report (full but "dirty" draft) |  |  | 2024-05-08 | This is for internal needs only and should not require a full edit or design effort.
Development of external information pieces, including donor deliverable |  |  | 2024-01-06 | These could be briefs, short reports, PPTs, or presentations. Each audience should be targeted with the most appropriate materials that are edited and designed.
Continuing MSA
TBD
|  | TOTAL LOE days (excluding operational planning) | 53-99
|  | Duration (months) | 3.5-5